# 2-Week Sprint + Final Polish Plan

EASER Research Data Hub — Internship Completion

July 14–31, 2026

## Overview

Compressed timeline: All major development tasks complete in 2 days, then 2 weeks of rigorous testing and polish.

## Sprint Week: 48-Hour Development Push (July 14–15)

Goal: Complete all core feature development and upload system fixes

Strategy: Use Opus prompts to handle heavy lifting in parallel; focus on:

All UI/UX refinements (design, responsiveness, polish)

File upload system overhaul (remove limits, robust handling)

GitHub publishing fixes

| Time | Primary Tasks (Opus) | Parallel Tasks |
| --- | --- | --- |
| Mon 7/14, AM | Opus Prompt 1: Complete UI/UX polish, responsive design, component refinements | — |
| Mon 7/14, PM | Opus Prompt 2: Upload system overhaul (remove 1GB limit, robust error handling, file validation) | Add institution logos |
| Tue 7/15, AM | Opus Prompt 3: GitHub publishing fixes + news integration from proyectoeaser.cl | PDF viewer & file downloads |
| Tue 7/15, PM | Integration testing, bug fixes, final smoke test of all features | Deploy to staging |

### Day 1 Tasks (July 14)

✓ UI/UX Polish (Opus Prompt 1)

Final styling, responsive design, all components matching design spec

Mobile & tablet layouts verified

Dark mode (if applicable)

✓ Upload System Overhaul (Opus Prompt 2)

Remove 1GB limit validation & messaging

Add robust error handling & user feedback

Support for large files (5GB+)

Graceful handling of Vercel timeout limits

### Day 2 Tasks (July 15)

✓ GitHub Publishing & News (Opus Prompt 3)

Fix GitHub publishing: only approved projects publish, correct folder structure

News sync endpoint from proyectoeaser.cl

Display latest news on homepage

✓ PDF Viewer & File Downloads

Implement PDF preview in browser

File download functionality for all file types

✓ Institution Logos (Parallel task)

Download 6 institution logos

Store in /public/logos/, integrate into UI

✓ Integration Testing & Smoke Test

All features working end-to-end

No critical bugs blocking deployment

Deploy to staging/production

## Polish & Testing Phase (July 16–31 | 2 weeks)

Goal: Rigorous testing, bug fixes, optimization, documentation

| Timeline | Focus | Key Activities |
| --- | --- | --- |
| Week 1 (7/16–7/22) | QA & bug fixes | Comprehensive testing of all workflows, user roles, file types. Fix any bugs found. Performance optimization. |
| Week 2 (7/23–7/31) | Final polish & handoff | Edge case testing, final performance verification, documentation updates, deployment checklist, team handoff |

## Key Success Metrics

By end of sprint (July 15):

All core features implemented and integrated

Upload system working for all file types & sizes

GitHub publishing correct

Platform deployed and accessible

By end of internship (July 31):

Zero critical bugs; all known issues documented

Mobile-responsive design verified on all browsers

Large file uploads tested (up to 5GB)

Documentation complete and accurate

Team fully trained and handoff complete

## Critical Path & Risk Mitigation

This aggressive timeline is achievable because:

Opus prompts handle most heavy coding work in parallel

Architecture is stable; focus is feature completeness, not redesign

Testing phase (2 weeks) provides buffer for bug fixes

If issues arise:

Non-critical features (news integration, logos) are lowest priority

Testing phase can absorb most bugs; prioritize upload system & publishing

Have fallback for any external API integrations (news feed, logos)

This plan trades development time pressure for thorough 2-week testing phase. The sprint is intense but focused; the remaining time ensures quality.